TRANSITIONAL SAFETY MANAGEMENT PLAN (TSMP)

Master Table of Contents & Commissioning / Handover Execution Plan

| Document Number: | TSMP-PLN-001 |
| --- | --- |
| Document Title: | Transitional Safety Management Plan |
| Version & Status: | 1.0 (Master Architecture - Work In Progress) |
| Jurisdiction & Governing Codes: | BC Energy Regulator (BCER), WorkSafeBC OHSR, TSBC, CSA Z276, ISO 45001 |
| Target Audience: | Owner Leadership, Operations & Commissioning, EPC Contractor, Regulators |

SECTION 1.0: PURPOSE, SCOPE & TRANSITION MILESTONES

1.1 Purpose & Execution Scope

•  1.1.1 Governance Bridge between EPC Construction Rules and Owner OSMM

•  1.1.2 Lifecycle Phases: Mechanical Completion (MC) -> Pre-Commissioning -> Commissioning -> Hydrocarbon Intro -> Handover

1.2 Dispersed / Subsystem Turnover Execution Model

•  1.2.1 Non-Linear System Handover Strategy (Early Utility Systems e.g., Instrument Air, Nitrogen, Power)

•  1.2.2 Interface Control between Energized Subsystems and Adjacent Active Construction Footprints

1.3 Statutory & Regulatory Approvals Gate

•  1.3.1 BCER Commissioning Consent & Testing Notifications

•  1.3.2 Technical Safety BC (TSBC) Operating Permits & Inspection Sign-Offs

SECTION 2.0: TRANSITIONAL ROLES, RESPONSIBILITIES & AUTHORITY MATRIX

2.1 WorkSafeBC Prime Contractor Governance during Transition

•  2.1.1 Owner Prime Contractor Overall Site Safety Authority

•  2.1.2 Owner Safety Oversight Structure in Multi-Employer Environment

2.2 EPC Contractor Oversight & Subcontractor Safety Alignment

•  2.2.1 EPC Construction Oversight Responsibilities on Un-Turned-Over Assets

•  2.2.2 Subcontractor Safety Alignment & Compliance Enforcement

2.3 Owner Operations & Commissioning Team Authority

•  2.3.1 Commissioning Manager & Area Isolation Authority Powers

•  2.3.2 Operations Permit Issuing Authority on Turned-Over Assets

2.4 Interface & Authority Matrix (RACIS Chart)

•  2.4.1 System Handover RACIS Matrix (Construction vs. Operations vs. Safety vs. EPC)

SECTION 3.0: CARE, CUSTODY, AND CONTROL (CCCC) & HANDOVER GATES

3.1 System Boundary Demarcation & Red Line Markings

•  3.1.1 System Demarcation P&ID Drawings & Color-Coded Piping Maps

•  3.1.2 Physical Boundary Flags, Barricades, and Signage Criteria

3.2 Joint System Walkdown & Punchlisting Protocol

•  3.2.1 Pre-Walkdown Documentation Verification (Hydrotest, NDE, Flush/Dry Records)

•  3.2.2 Joint Walkdown Team Composition (Owner Engineering, Operations, EPC, Quality)

3.3 Punchlist Categorization & Mandatory Closeout Gates

•  3.3.1 Category A Punch Items: Mandatory Closeout Prior to Mechanical Completion / Testing

•  3.3.2 Category B & C Punch Items: Closure Requirements Prior to Commodity Introduction

3.4 Transfer of Care, Custody, and Control (CCCC) Certificates

•  3.4.1 Formal Certificate Execution Sign-Off Workflow

•  3.4.2 Legal Asset Custody Transfer Logging

SECTION 4.0: TRANSITIONAL PERMIT TO WORK (PTW) PROTOCOL

4.1 Harmonized PTW Architecture

•  4.1.1 Retention of EPC Permit Form Factor to Preserve Workforce Familiarity

•  4.1.2 Transfer of Permitting Authority to Owner Operations for Turned-Over Systems

4.2 Daily Scope-Specific Permitting Execution

•  4.2.1 Mandatory Shift to Daily Permits for Turned-Over Systems

•  4.2.2 Daily Permit Issuance Workflows, Joint Field Risk Assessments & Gas Testing

4.3 Multi-Day 'Blanket Permit' Rules & Risk Screening

•  4.3.1 Eligible Low-Risk Work Scopes (Static Inspections, Non-Intrusive Civil/Painting)

•  4.3.2 Strict Exclusion Criteria & Revocation Triggers

4.4 PTW Interface & Cross-Boundary Permitting Controls

•  4.4.1 Work Originating in Construction Zones Impacting Live Systems (Dual Permitting Sign-Off)

SECTION 5.0: PHYSICAL, VISUAL & COMMUNICATION ISOLATION CONTROLS

5.1 Physical Energy Isolation (LOTO) Controls

•  5.1.1 Operations Color-Coded Lock System & Key Management

•  5.1.2 Specialty Positive Isolation: Blinds, Blanks, Double-Block & Bleed Standards

5.2 Visual Boundary Demarcation

•  5.2.1 High-Visibility Live System Tags, Color-Coded Blinding Tags, and Danger Signage

•  5.2.2 Physical Cable & Chain Isolation of Operations-Controlled Valves

5.3 Advance 'Livening Up' Notification Schedule

•  5.3.1 Mandatory 7-Day Advance Site-Wide Livening Notification & Map Broadcast

•  5.3.2 Mandatory 48-Hour Re-Notification & Area Supervisor Alignment

•  5.3.3 Mandatory 24-Hour Final Warning, Horn/Siren Broadcast & Physical Walkdown

5.4 Lockout/Tagout (LOTO) Custody Transfer Mechanics

•  5.4.1 Formal Cutting/Removal of EPC Construction Locks

•  5.4.2 Installation of Operations Master Locks on Centralized Lock Boxes

SECTION 6.0: SIMOPS MANAGEMENT & MULTI-LAYERED FIELD ASSURANCE

6.1 Dispersed System SIMOPS Hazard Analysis

•  6.1.1 SIMOPS Risk Matrix (Construction vs. Energized Utilities vs. Hydrocarbons)

•  6.1.2 Area-Specific SIMOPS Risk Mitigation Plans

6.2 Multi-Layered Field Assurance & Verification System

•  6.2.1 Safety Department Field Auditing & Formal Compliance Reporting

•  6.2.2 Supervisory Field Verification Tools & Daily Observation Checklists

•  6.2.3 Mandatory Stage & Action Gate Sign-Off Workflows

SECTION 7.0: MANDATORY IN-PERSON TRANSITION ORIENTATION & COMPETENCY

7.1 Transition Orientation Mandate

•  7.1.1 100% Mandatory Attendance for All Personnel On-Site Prior to System Energization

•  7.1.2 Passing Score Threshold & Badge Re-Authorization Protocol

7.2 In-Person Delivery & Verification Standards

•  7.2.1 Classroom In-Person Curriculum (Live System Identification, LOTO Rules, PTW Interface)

•  7.2.2 Written & Practical Comprehension Testing

7.3 Train-the-Trainer Program & Authorized Instructor Designation

•  7.3.1 Instructor Qualification Criteria & Approved Trainer List

SECTION 8.0: MANAGEMENT OF CHANGE (MOC) ON TURNED-OVER ASSETS

8.1 MOC Mandatory Triggers on Turned-Over Systems

•  8.1.1 Modification Rules for Pipe, Instrument, Control Logic, or Valve Re-Configuration

•  8.1.2 Temporary Modifications & Emergency MOC Protocols

8.2 Joint MOC Review Committee

•  8.2.1 Committee Composition (Engineering, Operations, Commissioning, Safety)

•  8.2.2 MOC Risk Assessment, Approval Sign-Off, and Red-Line Drawing Updates

8.3 Field Work Execution & Re-Testing Controls

SECTION 9.0: PRE-STARTUP SAFETY REVIEW (PSSR) & COMMODITY INTRODUCTION GATE

9.1 Pre-Commissioning & Testing Protocols

•  9.1.1 Nitrogen Purging, Dewatering, Drying, and Vacuum Testing Controls

•  9.1.2 Cryogenic Leak Testing & Tightness Verification Procedures

9.2 Pre-Startup Safety Review (PSSR) Gate Execution

•  9.2.1 Multidisciplinary PSSR Team Composition & Field Verification Checklists

•  9.2.2 PSSR Approval Certificate Sign-Off Workflow

9.3 Strict Punchlist Closure Gate

•  9.3.1 Mandatory 100% Closure of Category A, B, and C Punch Items Prior to Hydrocarbon Intro

SECTION 10.0: PHASED EMERGENCY MANAGEMENT & ICS TRANSITION

10.1 Phase 1 Emergency Response Structure (Construction & Pre-Commissioning)

•  10.1.1 Owner-Managed 3rd-Party Medical & Emergency Services Provider Role

•  10.1.2 Site Medical, Muster Point, and Construction Siren Operations

10.2 Phase 2 Emergency Response Structure (Commissioning & Testing)

•  10.2.1 Shared Dual Operations & Construction Incident Command System (ICS)

•  10.2.2 Dual Incident Commander Protocols & Unified Command Post

10.3 Phase 3 Emergency Response Structure (Hydrocarbon Introduction & Onward)

•  10.3.1 Transition to Sole Operations Incident Command

•  10.3.2 EPC & Construction Support Roles during Demobilization